## Sheet1
Workstream | Task | Priority | Proposed Owner | Deliverable / Acceptance | Dependencies | Notes
0) Design Alignment Sprint | Create AKS Compatibility Matrix (Flux sources, secrets engine, registry, admission, KEDA, quotas, observability) | P0 | You | Filled matrix: Allowed/Not Allowed/Defaults + notes | AKS docs
0) Design Alignment Sprint | Draft Guardrails (naming, repos, S/M/L, security posture) | P0 | You | 1-page Confluence guardrails | Compatibility Matrix
0) Design Alignment Sprint | Write ADRs (Flux SCM, secrets backend, registry choice, signing policy) | P0 | You | 4 short ADRs (Accepted/Pending) | Compatibility Matrix
0) Design Alignment Sprint | Open-questions list for AKS team + schedule 30-min read-out | P0 | You | Q&A sheet + meeting on calendar | Compatibility Matrix
A) Foundations & Repos | Create repos: ado-agent-image, ado-agent-kustomize | P0 | Colleague-A (image), Colleague-B (kustomize) | Repos with README, CODEOWNERS, branch policy | Guardrails
A) Foundations & Repos | Define SemVer + tagging policy (ban latest); document in READMEs | P0 | You | ADR + README snippet in both repos | —
A) Foundations & Repos | Registry topology (ACR/Nexus), enable immutability & retention, push/pull smoke test | P0 | Colleague-B | Can push/pull signed image from one region | AKS policy
B) Agent Image & CI | Author Dockerfile (non-root, ADO agent, PostgreSQL tools baked; no runtime installs) | P0 | Colleague-A | Local run proves agent registers and exits cleanly | —
B) Agent Image & CI | Implement graceful deregistration on SIGTERM in entrypoint | P0 | Colleague-A | Pod deletion removes agent from pool | Dockerfile
B) Agent Image & CI | CI pipeline: build → scan (fail on critical) → SBOM → sign (Cosign) → push | P0 | Colleague-A | Signed image :X.Y.Z published; SBOM attached | Registry ready
B) Agent Image & CI | Mirror/pin base image digests; document | P0 | Colleague-A | Digest list committed; mirror job works | Registry
C) Kustomize Manifests | Create base/ (Deployment std & heavy, SA/RBAC, env, emptyDir, requests/limits) | P0 | Colleague-B | kustomize build base validates | Guardrails
C) Kustomize Manifests | Add KEDA ScaledObject per pool (Azure Pipelines scaler) | P0 | Colleague-B | ScaledObjects validate (poolID placeholder) | AKS allows KEDA
C) Kustomize Manifests | Create overlays/<region>/{std,heavy} (image tag, pool names/IDs, scaling limits) | P0 | Colleague-B | kustomize build overlays/<region> renders clean | Namespace request
C) Kustomize Manifests | Wire PAT secret via Secret Store CSI / platform standard | P0 | Colleague-B | Pod reads PAT; rotation KB published | Platform secret engine | PAT for registration only
D) Flux GitOps | Confirm Flux controllers model (platform vs you) and bootstrap if needed | P0 | You + AKS team | Flux healthy in target cluster | AKS docs
D) Flux GitOps | Create Flux GitRepository source for kustomize repo | P0 | Colleague-B | Source reconciles; fetches main branch | Flux running
D) Flux GitOps | Create Flux Kustomization per region (path overlays/<region>, targetNamespace ado-agents) | P0 | Colleague-B | Kustomization applies; Deployments Available | Namespace exists
D) Flux GitOps | (Optional) Draft Image Automation (ImageRepository, ImagePolicy, ImageUpdateAutomation) | P1 | Colleague-B | YAML drafted (disabled) for later enablement | Decision/ADR | Manual PR bumps for MVP
E) Namespace as a Service | Produce per-region capacity ask (CPU/Mem for std + heavy + 20–30% headroom) | P0 | You | One-pager per region with numbers & rationale | S/M/Heavy sizing
E) Namespace as a Service | Submit namespace request (quotas, LimitRange defaults, PSA, NetworkPolicy egress allowlist) | P0 | You | Namespaces created; policy test pod passes | Capacity ask
E) Namespace as a Service | Verify KEDA availability & RBAC in namespace | P0 | Colleague-B | ScaledObject admitted; no errors | Namespace live
F) Identity & Secrets | Configure Workload Identity/OIDC service connection (runtime Azure auth) | P0 | Colleague-A | Sample pipeline calls Azure using OIDC | AKS/ADO config
F) Identity & Secrets | Define PAT rotation runbook (short-lived, minimal scope) | P0 | Colleague-B | KB with steps & schedule | Secret store
G) Observability & Alerts | Create dashboard (ADO queue wait, job success/fail; pod restarts/OOM, CPU throttle, image pull latency; KEDA replicas) | P0 | Colleague-A | Grafana dashboard shared with team | Platform observability access
G) Observability & Alerts | Add alerts (P95 queue breach, scale failure, OOMKilled, ImagePullBackOff) | P0 | Colleague-A | Alerts reach on-call; link runbooks | Dashboard
H) Migration & Rollout | Create ADO agent pools (pool-<region>-std, pool-<region>-heavy) and capture numeric pool IDs | P0 | Colleague-B | Pools visible; IDs in overlays | ADO perms
H) Migration & Rollout | Enable Flux for primary region; reconcile std & heavy pools | P0 | Colleague-B | Pods running; KEDA scales; heavy min=1 warm | Flux + namespace
H) Migration & Rollout | Map Dev pipelines/stages to pools (light→std, heavy→heavy) | P0 | Colleague-A | Dev cohort runs green; queue SLA met | Pools live
H) Migration & Rollout | Implement VM fallback for infra errors (probe then conditional requeue) | P0 | Colleague-A | Fallback tested; events logged | Pipeline edit
H) Migration & Rollout | Expand to next regions in waves (Dev→Test→Prod with approvals) | P0 | You (coordination) | Regions live; change log updated | Primary region stable
I) Security & Policy | Enforce minimum posture (non-root, seccomp, no privilege escalation, drop caps) via Kustomize patches | P0 | Colleague-B | Runtime verifies constraints applied | Base manifests
I) Security & Policy | Ensure CI signing & SBOM on every image; publish provenance | P0 | Colleague-A | Signed images only; SBOM attached to releases | CI pipeline
I) Security & Policy | (P1) Admission policy to verify signatures / CVE gates when platform ready | P1 | You + AKS team | Unsigned image denied in test namespace | Platform capability
J) Runbooks & Enablement | Write SRE runbooks (registration fail, image-pull, KEDA/HPA, OOM/throttle, proxy/DNS) | P0 | Colleague-B | Confluence pages with kubectl snippets | Observability
J) Runbooks & Enablement | Publish 'How to choose a pool' guide for app teams (YAML examples) | P0 | You | One-pager link shared | Pools live
J) Runbooks & Enablement | Deliver 45-min enablement (AKS + KEDA + Flux basics) | P0 | You | Session delivered; notes recorded | Runbooks