## Sheet1
Workstream / Phase | Area | Task (Ready to Assign) | Why / Outcome | Steps (What to do) | Recommended Defaults / Values | Proposed Owner (Role) | Priority | Dependencies | Acceptance Criteria
0) Design Alignment Sprint | Platform Alignment | Read AKS platform docs and fill the Compatibility Matrix | Align with what the platform actually supports before we build anything. | Skim, then deep dive; capture Allowed/Not Allowed/Defaults for Flux, secrets, registry, policies, quotas, observability. | Matrix columns: Capability, Option, Allowed?, Default, Notes/Links, Decision. | You | P0 | Platform documentation | Matrix completed and published in Confluence; links to source pages included.
0) Design Alignment Sprint | Guardrails | Publish project Guardrails (naming, repos, S/M/L pools, security posture) | Give the team a consistent baseline and prevent rework. | Write 1 page; circulate for quick +1; store at repo root and Confluence. | Naming: pool-<region>-std¦heavy; Namespace: ado-agents; No 'latest' tags; Non-root; Drop caps; Read-only rootfs where possible. | You | P0 | Compatibility Matrix | Guardrails page approved and referenced by repos.
0) Design Alignment Sprint | ADRs | Create ADRs for Flux Source SCM, Secrets backend, Registry, Signing policy | Record why we chose each path under platform constraints. | One-pagers: Context → Decision → Consequences → Next. Mark Pending if awaiting platform answer. | Default preference: Azure Repos for Flux; Key Vault CSI if offered; ACR with geo-rep; Cosign signing with keyless or key-pair. | You | P0 | Compatibility Matrix | ADRs committed; statuses set (Accepted/Pending).
0) Design Alignment Sprint | Open Questions | Prepare Q&A list and book 30-min read-out with AKS team | Close gaps quickly and unblock CI/CD work. | List the unknowns; propose our default; ask for confirm/deny; schedule call. | Unknowns to confirm: Flux image automation allowed? Secret engine? KEDA RBAC? Admission policies? Egress/Proxy CA? | You | P0 | Compatibility Matrix | Meeting held; answers merged into ADRs and Guardrails.
A) Foundations & Repos | Repositories | Create two repos: ado-agent-image and ado-agent-kustomize | Separation of concerns: image lifecycle vs environment/state. | Scaffold READMEs, CODEOWNERS, PR templates; enable branch policies. | Trunk-based; SemVer tags only; Owners: Image=Platform DB-Ops, Kustomize=Platform DB-Ops. | Colleague-A (image), Colleague-B (kustomize) | P0 | Guardrails | Repos created with policies enforced.
A) Foundations & Repos | Versioning | Define SemVer + tagging policy; ban mutable tags | Deterministic rollbacks and environment parity. | Document in README; enforce in CI (reject 'latest'). | Tags: X.Y.Z (release), X.Y (minor), X (major) optional; Pre-release: X.Y.Z-rc.N; No latest. | You | P0 | — | Policy merged; CI check in place.
A) Foundations & Repos | Registry | Stand up image registry and test push/pull | Ensure fast regional pulls and immutability. | Create repo; enable immutability & retention; test auth/pull from AKS region. | Preferred: ACR with geo-rep; Retention: 180d; Keep last 50 releases; Enable private link if mandated. | Colleague-B | P0 | Platform registry rules | Signed image pulled successfully from a pod in target region.
B) Agent Image & CI | Dockerfile | Author agent Dockerfile with baked tools | Eliminate 'missing package' incidents and drift. | Base → install ADO agent → install psql/pg_dump/pg_restore, pgBackRest, az, jq, curl → non-root → healthcheck → entrypoint. | Base pinned by digest; Non-root UID e.g. 10001; No runtime apt-get; Read-only rootfs if toolchain allows. | Colleague-A | P0 | Guardrails | Container registers agent and runs a sample job locally.
B) Agent Image & CI | Entrypoint | Implement graceful deregistration on SIGTERM | Avoid orphaned agents and pool clutter. | On start: config with PAT; On SIGTERM: 'config remove'; Log success; Exit 0. | Timeout 20–30s; retries x3; idempotent cleanup. | Colleague-A | P0 | Dockerfile | Killing pod removes agent from ADO pool; verified in logs.
B) Agent Image & CI | CI pipeline | Create CI: build → scan → SBOM → sign → push | Supply-chain security and auditability. | Build image; Trivy/Grype scan (fail CVSS≥9); Generate SBOM (CycloneDX/SPDX); Cosign sign; Push; Attach artifacts to release. | Block release on critical CVEs; Store digest in Git release notes. | Colleague-A | P0 | Registry ready | Signed image with SBOM published; CI badge green.
B) Agent Image & CI | Base image pinning | Mirror & pin base images by digest | Reproducibility and faster pulls. | Mirror upstream to registry; record digests; update Dockerfile FROM with @sha256. | Schedule monthly refresh; alert on CVEs for base image. | Colleague-A | P0 | Registry | FROM uses digest; digest list committed.
C) Kustomize + Flux | Base manifests | Create Kustomize base (Deployment std & heavy, SA/RBAC, env, emptyDir, requests/limits) | Single source of truth for all regions. | Add labels, annotations; set resource requests/limits; mount PAT secret; set ADO vars. | std: req 1 vCPU/2 Gi, lim 2 vCPU/4 Gi, emptyDir 15 Gi; heavy: req 4 vCPU/8 Gi, lim 6 vCPU/12 Gi, emptyDir 60 Gi. | Colleague-B | P0 | Guardrails | kustomize build base validates with no errors.
C) Kustomize + Flux | KEDA | Add KEDA ScaledObjects per pool (Azure Pipelines scaler) | Autoscale by pending ADO jobs per pool. | Create ScaledObject for std and heavy with poolID and org URL. | Polling 30s; Cooldown 120s; std min=0 max=12; heavy min=1 max=4; queueLength target=1. | Colleague-B | P0 | KEDA allowed in ns | ScaledObjects reconcile; HPA objects visible; test scale-up/down.
C) Kustomize + Flux | Region overlays | Create overlays per region (e.g., overlays/weu) with patches for pool names/IDs and image tag | Keep artifacts identical; change only values per region. | Patch image repo:tag, ADO_POOL names, poolIDs, KEDA maxReplicas. | Pool names: pool-<region>-std¦heavy; Example WEU: std max=12, heavy max=4. | Colleague-B | P0 | Base manifests | kustomize build overlays/<region> renders ready-to-apply YAML.
C) Kustomize + Flux | Secrets plumbing | Wire PAT secret via platform standard (Key Vault CSI / Vault) | Keep secrets out of Git and allow rotation. | Mount projected volume at /var/run/secrets/ado; document rotation steps. | PAT scope minimal; TTL ≤ 7d; rotation monthly or on demand; no PAT in env vars. | Colleague-B | P0 | Platform secrets model | Pod reads PAT; rotation tested successfully.
D) Flux GitOps | Flux bootstrap | Ensure Flux controllers are running and permitted to reconcile our ns | Enable GitOps deployments per region. | If platform-managed, just verify; otherwise install controllers in flux-system. | Source polling 1–5m; Kustomization wait=true; prune=true. | You + AKS Team | P0 | Platform decision | Flux components Healthy; events show successful sync.
D) Flux GitOps | Flux Source | Create Flux GitRepository for kustomize repo (Azure Repos/GitLab per platform) | Connect Git to cluster reconcilers. | Add source with branch=main; auth via SSH/PAT as allowed; set interval=1m. | Prefer SSH with deploy key; PAT only if mandated. | Colleague-B | P0 | Flux running | Source object Ready; revision updates on push.
D) Flux GitOps | Flux Kustomizations | Create one Flux Kustomization per region (targetNamespace: ado-agents) | Safe region-by-region rollout and health checks. | Point to overlays/<region>; add healthChecks for std & heavy deployments. | Timeout 5m; dependsOn if ordering required; remediation: retry. | Colleague-B | P0 | Namespace exists | Kustomizations Ready; Deployments Available after reconcile.
D) Flux GitOps | Image automation (optional) | Draft Flux ImageRepository/Policy/UpdateAutomation (disabled for MVP) | Enable auto-bump later without structure changes. | Create YAML with filter on SemVer and environment channel; keep disabled for now. | Manual PR bump for MVP; revisit after go-live. | Colleague-B | P1 | ADR decision | YAML exists in repo; feature flag noted for later enablement.
E) Namespace-as-a-Service | Capacity request | Prepare per-region namespace capacity request (CPU/Mem) | AKS team needs a number to create quotas and plan nodes. | Compute from planned std/heavy max replicas; add 20–30% headroom. | Templates: • Small (Dev): CPU 8 vCPU, Mem 16 Gi • Medium (Test): CPU 14 vCPU, Mem 28 Gi • Large (Prod MVP): CPU 20 vCPU, Mem 40 Gi | You | P0 | S/M/Heavy sizing | One-pager per region with chosen template and rationale.
E) Namespace-as-a-Service | Quota & LimitRange | Submit namespace request with ResourceQuota + LimitRange defaults | Prevent noisy-neighbour and enforce S/M/L shapes. | Ask AKS to set CPU/Mem quotas and default requests/limits that match std/heavy. | Default LimitRange: • std: req 1 vCPU/2 Gi, lim 2 vCPU/4 Gi • heavy: req 4 vCPU/8 Gi, lim 6 vCPU/12 Gi | You | P0 | Capacity request | Namespace created; kubectl describe shows quotas and limits as requested.
E) Namespace-as-a-Service | Policy & Egress | Request PSA, NetworkPolicy (deny-all + allowlist), and proxy/CA settings | Security baseline and reliable outbound to ADO/registry. | Submit list of endpoints and ports; include time/NTP, registry, dev.azure.com. | dev.azure.com/*; ACR/Nexus endpoints; NTP; corporate proxy. Provide NO_PROXY rules for cluster-local. | You | P0 | Platform security process | Policy test: allowed egress works; everything else blocked.
E) Namespace-as-a-Service | KEDA enablement | Confirm KEDA is installed and our ns can create ScaledObjects | Autoscaling hinges on this controller. | Create a dummy ScaledObject or validate CRD and permissions; agree on version. | PollingInterval 30s; Cooldown 120s; controller >= 2.12 recommended. | Colleague-B | P0 | Namespace live | kubectl get scaledobject shows objects; HPA appears when jobs queue.
F) Identity & Secrets | OIDC service connection | Enable Workload Identity/OIDC for pipelines that touch Azure | Eliminate long-lived credentials and secret sprawl. | Create federated identity; update ADO service connection; test az login via OIDC. | Scope SP to least-privilege; rotate credentials via policy. | Colleague-A | P0 | Platform IAM model | Sample pipeline runs 'az group list' without secrets in variables.
F) Identity & Secrets | PAT rotation runbook | Document and test PAT rotation for agent registration | Short-lived tokens reduce risk; avoid outages on expiry. | Define PAT scope and TTL; store in secret engine; test rotation with zero downtime. | PAT TTL ≤ 7 days; rotate monthly or on demand; no PAT in env vars. | Colleague-B | P0 | Secrets engine decision | KB published; rotation executed once and logged.
G) Observability & Alerts | Dashboards | Publish minimal dashboards for ADO + K8s + KEDA | Fast troubleshooting and SLO tracking. | Create Grafana board per region; link from runbooks. | Panels: ADO queue P95, success rate; Pod restarts/OOM; CPU throttle; Image pull latency; KEDA replicas. | Colleague-A | P0 | Access to metrics | Dashboard link shared; P95 queue visible for last 7 days.
G) Observability & Alerts | Alerts | Add actionable alerts with runbook links | Page on symptoms we can act on quickly. | Configure alert rules in platform tool; include labels and links. | Thresholds: P95 queue > 60s (5m), OOMKilled > 0, ImagePullBackOff > 0, KEDA scale failure detected. | Colleague-A | P0 | Dashboards | Alerts fire to on-call; test notifications received.
H) Migration & Rollout | Create ADO pools | Create pools for primary region and capture numeric pool IDs | Pools are the scaling targets for KEDA and where pipelines bind. | Create pool-<region>-std and pool-<region>-heavy; record IDs in overlays. | Name pools region-qualified to keep future multi-region easy. | Colleague-B | P0 | ADO permissions | Pools visible in ADO; IDs committed to repo (not secrets).
H) Migration & Rollout | Enable Flux for primary region | Reconcile std & heavy in the first namespace | Get real pods running to start testing. | Apply flux/source and flux/kustomization for region; watch objects become Ready. | Heavy min=1 warm; std min=0; verify scale-out on queued jobs. | Colleague-B | P0 | Namespace + Flux | Both deployments Available; KEDA scales when jobs queue.
H) Migration & Rollout | Map Dev pipelines to pools | Run a Dev cohort on std/heavy pools with VM fallback | Prove stability before expanding. | Tag stages: light→std; heavy→heavy; add probe stage and conditional VM rerun for infra errors. | Infra errors only trigger fallback; functional failures do not. | Colleague-A | P0 | Pools live | N consecutive green runs; queue SLA ≤ 60s during business hours.
H) Migration & Rollout | Region waves | Roll out to next regions (Dev→Test→Prod) | Gradual expansion with approvals and telemetry. | Copy overlays; add Flux Kustomization per region; gate prod on smoke tests. | Runbooks ready; team on-call aware of rollout plan. | You | P0 | Primary region stable | Regions live with change log updated; no Sev-1 in rollout window.
I) Security & Policy | Runtime posture | Enforce minimum pod security via Kustomize patches | Reduce container escape and privilege risks. | Set runAsNonRoot, drop ALL caps, disallow privilege escalation, seccomp=RuntimeDefault. | If toolchain requires write rootfs, mount only what’s needed; prefer read-only when possible. | Colleague-B | P0 | Base manifests | kubectl describe shows securityContext applied; CIS checks pass.
I) Security & Policy | Supply chain | Ensure every image is scanned, signed, and has SBOM | Meet audit and rollback needs; block risky builds. | Integrate scanner; fail CVSS≥9; sign with Cosign; attach SBOM to release; record digest in ADR/release notes. | Keep keys in HSM/KMS or use keyless if platform supports. | Colleague-A | P0 | CI pipeline | Unsigned images are blocked by CI; signed images present in registry with SBOM.
I) Security & Policy | Admission (later) | Adopt signature verification/CVE gates when platform supports | Enforce at cluster gate, not only in CI. | Work with AKS team to enable Gatekeeper/Kyverno policies for Cosign verify. | Pilot in non-prod; then promote. | You + AKS Team | P1 | Platform feature | Unsigned image denied in test ns; policy exceptions documented.
J) Runbooks & Enablement | Runbooks | Publish SRE runbooks with kubectl snippets and decision trees | Shorten MTTR and standardize troubleshooting. | Write: registration fail, image-pull errors, KEDA/HPA issues, OOM/throttle, proxy/DNS; add links to dashboards. | Use copy-paste commands; include common error messages and fixes. | Colleague-B | P0 | Observability live | Runbooks reviewed by SRE; linked in alerts.
J) Runbooks & Enablement | Pool selection guide | Create 'How to choose a pool' for app teams | Reduce questions and mis-routing of jobs. | Explain std vs heavy; include YAML examples; note region-qualified pool names. | Rule of thumb: RSS<2Gi & artifacts<10Gi → std; else heavy. | You | P0 | Pools live | Page published; linked from onboarding docs.
J) Runbooks & Enablement | Enablement session | Deliver 45-min training (AKS + KEDA + Flux basics) | Ensure on-call can operate day-1. | Slides + live demo; Q&A; record session. | Cover probe/fallback pattern and common alerts. | You | P0 | Runbooks | Session recorded; attendees confirm readiness.